## ✨Girlypops✨ Project Information
ITSC-3155 Software Engineering
✨Girlypops✨ Project Information
GitHub Link
Team Members: Bindu Harini Gunturi, Nyx Stark, Kaleiah Mcpherson, Gavin Binkley, Smriti Bhemireddy

## Product Backlog
ITSC-3155 Software Engineering
✨Girlypops✨ Product Backlog
STORY ID | FEATURE NAME | PRIORITY | POINTS | DEFINE USER STORY | ASSIGNED TO SPRINT | SPRINT #
1 | Create Menu items | High | 5 | Yes | Yes | 1
2 | Delete Menu Items | High | 3 | Yes | Yes | 1
3 | Update Menu Items | High | 3 | Yes | Yes | 1
4 | Insufficient ingredient alert | High | 8 | Yes | Yes | 1
5 | Manually adjust inventory | Medium | 3 | Yes | Yes | 2
6 | Auto-disable out-of-stock items | Medium | 5 | Yes | Yes | 2
7 | View all orders | High | 3 | Yes | Yes | 1
8 | View order details | High | 3 | Yes | Yes | 1
9 | Filter orders by date range | Medium | 3 | Yes | Yes | 2
10 | Identify low-performing dishes | Medium | 5 | Yes | Yes | 2
11 | View complaint/review reasons | Medium | 5 | Yes | Yes | 2
12 | Create/manage promo codes | Medium | 5 | Yes | Yes | 2
13 | View promo code performance | Low | 3 | Yes | No
14 | Daily revenue total | High | 3 | Yes | Yes | 1
15 | Revenue trends over time | Low | 5 | Yes | No
16 | Place an order without an account | High | 5 | Yes | Yes | 1
17 | Optional account creation | Low | 3 | Yes | No
18 | Pay for an order online | High | 8 | Yes | Yes | 1
19 | Pay cash on delivery/pickup | Medium | 3 | Yes | Yes | 2
20 | Choose takeout or delivery | High | 3 | Yes | Yes | 2
21 | Estimated ready/delivery time | Medium | 3 | Yes | Yes | 2
22 | Track orders / view order details | High | 5 | Yes | Yes | 1
23 | Real-time status updates | Medium | 5 | Yes | Yes | 2
24 | Search/filter by dietary type | Medium | 5 | Yes | Yes | 2
25 | Keyword search | Medium | 3 | Yes | Yes | 2
26 | Rate and review a dish | Medium | 5 | Yes | Yes | 2
27 | View other customers' reviews | Low | 3 | Yes | No
28 | Apply a promo code at checkout | Medium | 3 | Yes | Yes | 2

## User Stories
ITSC-3155 Software Engineering
✨Girlypops✨ User Stories
ID | FEATURE | AS A <type of user> | I WANT TO <perform some task> | SO THAT <achieve some goal> | FINAL STORY | PRIORITY | STORY POINT
1 | Create Menu items | Restaurant Manager | create new menu items | customers can see and order new dishes | As a Restaurant Manager, I want to create new menu items so that customers can see and order new dishes. | High | 5
2 | Delete Menu Items | Restaurant Manager | remove menu items | discontinued dishes no longer appear to cusomters | As a Restaurant Manager, I want to remove menu items so that discontinued dishes no longer appear to customers. | High | 3
3 | Update Menu Items | Restaurant Manager | edit menu items | the menu stays accurate | As a Restaurant Manager, I want to edit menu items so that the menu stays accurate. | High | 3
4 | Insufficient ingredient alert | Restaurant Employee | receive alerts when ingredients are running low | employees know when to restock | As a Restaurant Employee, I want to receive alerts when ingredients are running low so that employees know when to restock. | High | 8
5 | Manually adjust inventory | Restaurant Manager | manually update inventory quantities | counts stay accurate after deliveries or waste | As a Restaurant Manager, I want to manually update inventory quantities so that counts stay accurate after deliveries or waste. | Medium | 3
6 | Auto-disable out-of-stock items | Restaurant Manager | automatically hide unavailable menu items | customers can't order dishes that there isn't ingredients for | As a Restaurant Manager, I want to automatically hide unavailable menu items so that customers can't order dishes that there isn't ingredients for. | Medium | 5
7 | View all orders | Restaurant Employee | view all customer orders | I can monitor what orders have been made | As a Restaurant Employee, I want to view all customer orders so that prepare them in the order they were received. | High | 3
8 | View order details | Restaurant Employee | view complete order information | I can see itemized details, special instructions, order type, and payment status | As a Restaurant Employee, I want to view complete order information so that I can see itemized details, special instructions, order type, and payment status | High | 3
9 | Separate current orders vs completed | Restaurant Employee | filter orders by date | I can analyze sales during specific time periods | As a Restaurant Employee, I want to filter orders by date so that I can analyze sales during specific time periods. | Medium | 3
10 | Identify low-performing dishes | Restaurant Manager | identify dishes with low sales | I can decide how to improve the restaurant menu | As a Restaurant Manager, I want to identify dishes with low sales so that I can improve the restaurant menu. | Medium | 5
11 | View complaint/review reasons | Restaurant Manager | review customer complaints and feedback | I can improve customer satisfaction | As a Restaurant Manager, I want to review customer complaints and feedback so that I can improve customer satisfaction. | Medium | 5
12 | Create/manage promo codes | Restaurant Manager | create and manage promotional codes | I can offer discounts and promotions | As a Restaurant Manager, I want to create and manage promotional codes so that I can offer discounts and promotions. | Medium | 5
13 | View promo code performance | Restaurant Manager | view promo code usage statistics | I can evaluate the effectiveness of promotions | As a Restaurant Manager, I want to view promo code usage statistics so that I can evaluate the effectiveness of promotions. | Low | 3
14 | Daily revenue total | Restaurant Manager | view total daily revenue | I can monitor daily business performance | As a Restaurant Manager, I want to view total daily revenue so that I can monitor daily business performance. | High | 3
15 | Revenue trends over time | Restaurant Manager | analyze revenue trends | I can make informed business decisions and spot trends | As a Restaurant Manager, I want to analyze revenue trends so that I can make informed business decisions and spot trends. | Low | 5
16 | Place an order without an account | Customer | place an order as a guest | I can order food quickly without registering | As a Customer, I want to place an order as a guest so that I can order food quickly without registering. | High | 5
17 | Optional account creation | Customer | create an account if I choose | I can save my order history and personal information | As a Customer, I want to create an account if I choose so that I can save my order history and personal information. | Low | 3
18 | Pay for an order online | Customer | securely pay online | my order is completed quickly | As a Customer, I want to securely pay online so that my order is completed quickly. | High | 8
19 | Pay cash on delivery/pickup | Customer | pay with cash when receiving my order | I can use my preferred payment method | As a Customer, I want to pay with cash when receiving my order so that I can use my preferred payment method. | Medium | 3
20 | Choose takeout or delivery | Customer | choose between takeout and delivery | I receive my food the way I prefer | As a customer, I want to choose between takeout and delivery so that I can use my preferred payment mechod at checkout | High | 3
21 | Estimated ready/delivery time | Customer | see an estimated preparation or delivery time | I know when to expect my order | As a customer, I want to see the estimated preparation or delivery time so that I know when to expect my order. | Medium | 3
22 | Track orders / view order details | Customer | view my order details and current status | I always know the progress of my order | As a customer, I want to track my order and view its details so that I always know its current status. | High | 5
23 | Real-time status updates | Customer | receive real-time updates | I stay informed throughout the order process | As a customer, I want to receive real-time status updates so that I stay informed throughout the order process. | Medium | 5
24 | Search/filter by dietary type | Customer | filter menu items by dietary preferences | I can quickly find food that meets my dietary needs | As a customer, I want to filter menu items by dietary preferences so that I can quickly find food that meets my needs. | Medium | 5
25 | Keyword search | Customer | search the menu using keywords | I can quickly find specific dishes | As a customer, I want to search the menu using keywords so that I can quickly find specific dishes. | Medium | 3
26 | Rate and review a dish | Customer | leave ratings and reviews | I can share my dining experience | As a customer, I want to rate and review dishes so that I can share my dining experience with others. | Medium | 5
27 | View other customers' reviews | Customer | read reviews from other customers | I can make informed ordering decisions | As a customer, I want to read reviews from other customers so that I can make informed ordering decisions. | Low | 3
28 | Apply a promo code at checkout | Customer | apply a promo code during checkout | I can receive available discounts | As a customer, I want to apply a promo code during checkout so that I can receive available discounts on my order. | Medium | 3
Total | [6 empty] | 116