## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog - Sprint 1
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1 - Create Menu Items | 5 | [8 empty] | Done
Set up FastAPI project skeleton, requirements.txt and feature-branch workflow |  | Smriti Bhemireddy | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Build MenuItem model / menu_items table (item_id PK, price, dietary_type, is_available) |  | Kaleiah Mcpherson | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Add MenuItemCreate/Update/response schemas and POST /menuitems route |  | Kaleiah Mcpherson | 3 | 2.5 | 2 | 1 | 0.5 | 0 | 0 |  | 0
Write test_menu_items.py create and validation tests |  | Kaleiah Mcpherson | 2 | 1.5 | 1 | 0.5 | 0 | 0 | 0 |  | 0
User Story #2 - Delete Menu Items | 3 | [8 empty] | Done
Implement delete() controller with 404 on unknown item_id |  | Kaleiah Mcpherson | 2 | 1.5 | 1 | 0.5 | 0 | 0 | 0 |  | 0
Add DELETE /menuitems/{item_id} route |  | Kaleiah Mcpherson | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Add ON DELETE CASCADE to the menu_item_inventory link rows |  | Bindu Harini Gunturi | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0 |  | 0
Add delete and delete-404 tests |  | Kaleiah Mcpherson | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0 |  | 0
User Story #3 - Update Menu Items | 3 | [8 empty] | Done
Implement update() with partial updates via exclude_unset |  | Kaleiah Mcpherson | 2 | 1.5 | 1 | 0.5 | 0 | 0 | 0 |  | 0
Add PUT /menuitems/{item_id} route |  | Kaleiah Mcpherson | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Support the is_available toggle so dishes can be hidden |  | Gavin Binkley | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0 |  | 0
Add update and update-404 tests |  | Kaleiah Mcpherson | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0 |  | 0
User Story #4 - Insufficient Ingredient Alert | 8 | [8 empty] | Done
Build Inventory model (ingredient_id, quantity, minimum_quantity, unit) |  | Bindu Harini Gunturi | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Inventory CRUD controller and /inventory router registered in index.py |  | Bindu Harini Gunturi | 4 | 3 | 2.5 | 1.5 | 1 | 0.5 | 0 |  | 0
GET /inventory/alerts low-stock query declared before /{item_id} |  | Bindu Harini Gunturi | 3 | 2.5 | 2 | 1 | 0.5 | 0 | 0 |  | 0
test_inventory_alerts.py - low stock, equal-to-minimum, empty, multiple |  | Bindu Harini Gunturi | 2.5 | 2.5 | 2.5 | 2 | 1 | 0.5 | 0 |  | 0
User Story #7 - View All Orders | 3 | [8 empty] | Done
Rewrite the orders controller stub against the real Order model (PK orderID) |  | Gavin Binkley | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
read_all()/read_one() plus GET /orders and GET /orders/{order_id} |  | Gavin Binkley | 2 | 1.5 | 1 | 0.5 | 0 | 0 | 0 |  | 0
404 handling for unknown orderID |  | Gavin Binkley | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
test_orders.py read-all, read-one and 404 tests |  | Gavin Binkley | 2 | 2 | 2 | 1.5 | 1 | 0.5 | 0 |  | 0
User Story #8 - View Order Details | 3 | [8 empty] | Carried to Sprint 2
Create the OrderItem model (order_details) linking orders to menu_items |  | Gavin Binkley | 3 | 2.5 | 2 | 1 | 0.5 | 0 | 0 |  | 0
OrderDetail Base/Create/Update schemas and the /orderdetails router |  | Gavin Binkley | 2.5 | 2 | 1.5 | 1 | 0 | 0 | 0 |  | 0
test_order_details.py CRUD coverage |  | Gavin Binkley | 2 | 2 | 2 | 1.5 | 1 | 0.5 | 0 |  | 0
Add special_instructions to each line item (NOT FINISHED - moved to Sprint 2) |  | Gavin Binkley | 2 | 2 | 2 | 1.5 | 1 | 1 | 1 |  | 1
User Story #14 - Daily Revenue Total | 3 | [8 empty] | Done
Join payments to orders so revenue can be aggregated by order date |  | Nyx Stark | 2.5 | 2 | 1.5 | 1 | 0 | 0 | 0 |  | 0
GET /reports/revenue/daily?date= endpoint |  | Nyx Stark | 2 | 2 | 2 | 1.5 | 1 | 0.5 | 0 |  | 0
Restrict the total to payments with status 'paid' |  | Nyx Stark | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0 |  | 0
test_revenue_reports.py daily-total and zero-day tests |  | Nyx Stark | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0 |  | 0
User Story #16 - Place An Order Without An Account | 5 | [8 empty] | Done
Customer model with hasAccount flag and email-validated schemas |  | Nyx Stark | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
customers controller and /customers router |  | Nyx Stark | 3 | 2.5 | 2 | 1 | 1 | 0.5 | 0 |  | 0
Make orders.customerID nullable so guests can check out |  | Nyx Stark | 2 | 1.5 | 1 | 0.5 | 0 | 0 | 0 |  | 0
test_customers.py including the invalid-email 422 case |  | Nyx Stark | 2 | 2 | 2 | 1.5 | 1 | 0.5 | 0 |  | 0
User Story #18 - Pay For An Order Online | 8 | [8 empty] | Done
Payment model (paymentID, paymentMethod, paymentStatus) with FK to orders |  | Bindu Harini Gunturi | 3 | 1.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
payments controller and /payments router |  | Bindu Harini Gunturi | 4 | 3 | 2.5 | 1.5 | 1 | 0.5 | 0 |  | 0
Payment status transitions: pending -> paid -> refunded |  | Bindu Harini Gunturi | 3 | 3 | 2.5 | 2.5 | 1.5 | 0.5 | 0 |  | 0
test_payments.py against a real seeded order |  | Bindu Harini Gunturi | 2.5 | 2.5 | 2.5 | 2 | 1 | 0.5 | 0 |  | 0
User Story #22 - Track Orders / View Current Status | 5 | [8 empty] | Carried to Sprint 2
Confirm orderStatus, orderType and estimatedTime columns on Order |  | Smriti Bhemireddy | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Status changes through PUT /orders/{order_id} |  | Smriti Bhemireddy | 2.5 | 2 | 1.5 | 1 | 0 | 0 | 0 |  | 0
Register every router in index.py and verify /docs renders |  | Smriti Bhemireddy | 2 | 1.5 | 1 | 0.5 | 0 | 0 | 0 |  | 0
Dedicated GET /orders/{order_id}/tracking view (NOT FINISHED - moved to Sprint 2) |  | Smriti Bhemireddy | 3 | 3 | 2.5 | 2 | 2 | 1.5 | 1 |  | 1
TOTAL | 46