# Sprint Review — Sprint 1 (Restaurant Ordering System)

## Sprint goals

Include the sprint goals set during sprint planning and evaluate progress as a team.

Goal 1 - Stand up the FastAPI service and the menu management slice

- All five of us can run the API locally with uvicorn api.main:app --reload and /docs renders with no mapper or import errors.

- Menu items support full create, read, update and delete through /menuitems.

- test_menu_items.py passes with create, read-all, read-one, update, delete and 404 coverage.

Goal 2 - Give restaurant staff visibility into orders and inventory

- /orders and /orderdetails return itemized orders with per-item quantities.

- GET /inventory/alerts flags every ingredient sitting at or below its minimum quantity.

- Employees can move an order forward with PUT /orders/{order_id}.

Goal 3 - Let a customer get all the way through checkout

- A guest can place an order without a customer account because orders.customerID is nullable.

- /payments records an online payment and moves it from pending to paid.

- GET /reports/revenue/daily totals only the payments whose status is paid.

## Demos

| Demo | Feedback |
| --- | --- |
| Menu item CRUD through /docs - create a dish, edit its price, delete a discontinued one (Stories 1, 2, 3) | Kaleiah demoed. The team asked why a negative price is accepted - no value validation exists yet. Logged as a fix for Sprint 2. |
| Low-stock alert - drop an ingredient below its minimum and call GET /inventory/alerts (Story 4) | Bindu demoed. Nyx asked whether a dish should hide itself automatically when an ingredient runs out. That is Story 6, already scheduled for Sprint 2. |
| Guest checkout - create a customer-less order, attach line items, pay online (Stories 16, 18) | Nyx and Bindu demoed together. Gavin pointed out that the client is still sending totalPrice, so the server trusts whatever number it is given. Added to Sprint 2. |
| Order list, status update and daily revenue total (Stories 7, 14, 22) | Gavin and Smriti demoed. The team agreed a plain PUT on the order is not really order tracking, so Story 22 cannot be accepted as done. |

## Complete tasks

Mark work items “Done” that met acceptance criteria. For items that need more work, determine if they will move to the next sprint or back to the backlog.

- Done - 38 of the 46 committed story points were accepted:

  - Story 1 (5 pts) Create menu items - POST /menuitems with schema validation.

  - Story 2 (3 pts) Delete menu items - DELETE /menuitems/{item_id} with 404 handling.

  - Story 3 (3 pts) Update menu items - PUT /menuitems/{item_id} with partial updates.

  - Story 4 (8 pts) Insufficient ingredient alert - GET /inventory/alerts.

  - Story 7 (3 pts) View all orders - GET /orders and GET /orders/{order_id}.

  - Story 14 (3 pts) Daily revenue total - GET /reports/revenue/daily.

  - Story 16 (5 pts) Place an order without an account - guest checkout works end to end.

  - Story 18 (8 pts) Pay for an order online - /payments with pending, paid and refunded states.

- Not accepted - 8 points move to Sprint 2 rather than back to the product backlog:

  - Story 8 (3 pts) View order details - line items and quantities work, but special_instructions was never added to the order_details table, so an employee still cannot see what the customer asked for.

  - Story 22 (5 pts) Track orders - status is readable from GET /orders/{order_id}, but there is no dedicated tracking view, which is what the story actually asks for.

## Upcoming

Add action items coming out of the sprint review meeting.

- Carry Stories 8 and 22 into Sprint 2 as the first two items, ahead of any new work.

- Stop trusting the client-supplied totalPrice - recalculate the order total server-side from the line items and the applied promo code.

- Placing or changing an order needs to decrement ingredient stock, and reject the change when there is not enough stock.

- Add value validation so negative prices, quantities and minimums are rejected instead of stored.

- Kaleiah, Nyx, Gavin and Bindu are leaving the project after this sprint. Smriti will own the remaining backlog, so Sprint 2 was re-estimated for a single developer.