## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog - Sprint 2
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #8 (carryover) - View Order Details | 3 | [8 empty] | Done
Add the special_instructions column to order_details and migrate ros.db |  | Smriti Bhemireddy | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 0
Expose special_instructions in the schemas with quantity >= 1 validation |  | Smriti Bhemireddy | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 0
Tests for special instructions and quantity validation |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
User Story #22 (carryover) - Track Orders / View Current Status | 5 | [8 empty] | Done
OrderTracking response schema (status, type, estimated time, date, total) |  | Smriti Bhemireddy | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 0
GET /orders/{order_id}/tracking controller function and route |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
test_order_tracking.py including 404 for an unknown order |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
User Story #5 - Manually Adjust Inventory | 3 | [8 empty] | Done
PUT /inventory/{ingredient_id} manual quantity adjustment |  | Smriti Bhemireddy | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 0
Reject negative quantity and minimum_quantity with 422 |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
test_inventory.py manual-adjustment and 404 tests |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
User Story #6 - Auto-Disable Out-Of-Stock Items | 5 | [8 empty] | Done
menu_item_inventory link-table CRUD on the composite key |  | Smriti Bhemireddy | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 0
POST /menuitems/recompute-availability using quantity_required |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Hook the recompute into inventory PUT plus test_menu_auto_disable.py |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Deduct and restore ingredient stock on order line-item changes (409 when short) |  | Smriti Bhemireddy | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0 |  | 0
test_inventory_deduction.py - deduct, restore, insufficient stock |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
User Story #9 - Filter Orders By Date Range | 3 | [8 empty] | Done
GET /orders?start_date=&end_date= with inclusive day bounds |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Handle one-sided bounds and empty ranges |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
test_orders_filter_date.py - 5 cases |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
User Story #10 - Identify Low-Performing Dishes | 5 | [8 empty] | Done
GET /reports/low-performing aggregating average rating and order counts |  | Smriti Bhemireddy | 1.5 | 1.5 | 1 | 0.5 | 0 | 0 | 0 |  | 0
Configurable max_avg_rating and max_order_count thresholds |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
test_low_performing_dishes.py - 4 cases |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
User Story #11 - View Complaint / Review Reasons | 5 | [8 empty] | Done
Reviews CRUD (PK reviewID) and the /reviews router |  | Smriti Bhemireddy | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 0
Surface complaint comments (rating <= 2) inside the low-performing report |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
test_reviews.py including the invalid-rating 422 case |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
User Story #12 - Create / Manage Promo Codes | 5 | [8 empty] | Done
PromoCode model with a string PK and managerID foreign key |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
promo_codes controller and /promocodes/{promo_code} routes |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
test_promo_codes.py - deactivate, change discount, 404s |  | Smriti Bhemireddy | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 |  | 0
User Story #19 - Pay Cash On Delivery / Pickup | 3 | [8 empty] | Done
Support a cash paymentMethod alongside card payments |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Allow the pending -> paid transition at pickup or delivery |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Payment-method tests |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
User Story #20 - Choose Takeout Or Delivery | 3 | [8 empty] | Done
Validate orderType on order create and update |  | Smriti Bhemireddy | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Return orderType in order responses and in the tracking view |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Order-type tests |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
User Story #21 - Estimated Ready / Delivery Time | 3 | [8 empty] | Done
Surface estimatedTime through order create and update |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Include estimatedTime in the tracking response |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Estimated-time tests |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
User Story #23 - Real-Time Status Updates | 5 | [8 empty] | Done
Status transition handling through PUT /orders/{order_id} |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Reflect the latest status in GET /orders/{order_id}/tracking |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Status-update tests |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
User Story #24 - Search / Filter By Dietary Type | 5 | [8 empty] | Done
GET /menuitems?dietary_type= filter |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Make the filter combinable with keyword search |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
test_menu_search.py dietary cases |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
User Story #25 - Keyword Search | 3 | [8 empty] | Done
GET /menuitems?q= searching name and description |  | Smriti Bhemireddy | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 |  | 0
Case-insensitive partial matching |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Keyword-search tests including the empty-result case |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
User Story #26 - Rate And Review A Dish | 5 | [8 empty] | Done
Review create with 1-5 rating validation and customer / menu item FKs |  | Smriti Bhemireddy | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
Validate that the reviewed dish and customer exist before saving |  | Smriti Bhemireddy | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 |  | 0
Review-creation tests |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
User Story #28 - Apply A Promo Code At Checkout | 3 | [8 empty] | Done
POST /promocodes/apply validating active and non-expired codes |  | Smriti Bhemireddy | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 |  | 0
Recompute order totals server-side from line items and the promo discount |  | Smriti Bhemireddy | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0 |  | 0
test_promo_apply.py and test_order_totals.py |  | Smriti Bhemireddy | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 |  | 0
User Story #27 (added mid-sprint) - Read Other Customers' Reviews | 3 | [8 empty] | Done
GET /reviews?item_id= filter so reviews can be read per dish |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
test_reviews_by_dish.py |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
User Story #15 (added mid-sprint) - Revenue Trends Over Time | 5 | [8 empty] | Done
GET /reports/revenue/trends?start_date=&end_date= aggregation |  | Smriti Bhemireddy | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 |  | 0
Reject inverted ranges with 400, plus trend tests |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | 0
User Story #17 (added mid-sprint) - Optional Account Creation | 3 | [8 empty] | Done
hasAccount flag honoured on customer create and update |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Account-creation tests |  | Smriti Bhemireddy | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0
Technical Task - Test Harness, Seed Data And Documentation | [9 empty] | Done
Isolated in-memory SQLite test harness (TESTING switch and conftest fixtures) |  | Smriti Bhemireddy | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 0
api/seed.py demo data across all 12 tables plus test_seed.py |  | Smriti Bhemireddy | 1.5 | 1.5 | 1 | 0.5 | 0 | 0 | 0 |  | 0
README, FEATURES.md, PROJECT_TASKS.md and TEST_PLAN.md |  | Smriti Bhemireddy | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 |  | 0
TOTAL | 75