# Sprint Review — Sprint 2 (Restaurant Ordering System)

## Sprint goals

Include the sprint goals set during sprint planning and evaluate progress as a team.

Goal 1 - Close out the Sprint 1 carryover before starting anything new

- order_details carries special_instructions end to end: model, schema, API and tests.

- GET /orders/{order_id}/tracking returns status, order type, estimated time, order date and total.

- Stories 8 and 22 are accepted, so nothing carries into a third sprint.

Goal 2 - Finish every remaining story in the product backlog

- All 14 stories committed to Sprint 2 are delivered, and Stories 15, 17 and 27 are pulled in once the surrounding work made them cheap.

- 66 endpoints are exposed across the 12 tables and all of them appear in /docs.

- Reporting covers daily revenue, revenue trends over time and low-performing dishes with their complaint comments.

Goal 3 - Make the server, not the client, the source of truth

- Order totals are recalculated server-side from the line items and the applied promo code, so the client can no longer set totalPrice.

- Adding, changing or deleting a line item deducts or restores ingredient stock, and returns 409 when there is not enough stock.

- Negative prices, quantities and minimum quantities are rejected with 422.

Goal 4 - Keep the suite green and the project reproducible

- The full pytest suite runs against an isolated in-memory SQLite database and never touches the dev database.

- python -m api.seed fills all 12 tables with demo data covering low stock, guest orders, promos, paid revenue and low ratings.

- README.md, FEATURES.md, PROJECT_TASKS.md and TEST_PLAN.md all match the code that shipped.

## Demos

| Demo | Feedback |
| --- | --- |
| Sprint 1 carryover - special instructions on a line item, and GET /orders/{order_id}/tracking (Stories 8, 22) | Demoed solo. Both carryover stories accepted. Decision made to keep the tracking response read-only so it cannot be used to mutate an order. |
| Inventory - manual adjustment, low-stock alert, and POST /menuitems/recompute-availability (Stories 5, 6) | Confirmed a dish flips to is_available = false as soon as a linked ingredient drops below its quantity_required, and the recompute also fires from the inventory PUT. |
| Server-side totals - add line items, apply a promo with POST /promocodes/apply, watch totalPrice recalculate (Stories 12, 28) | Confirmed the client can no longer dictate the total, that an inactive or expired code is rejected, and that the discount floors at 0 instead of going negative. |
| Inventory deduction - place an order that exceeds available stock and get a 409 back | Confirmed the stock is deducted on create, restored on delete, and adjusted by the difference when a quantity is edited. |
| Menu search and reviews - ?dietary_type=, ?q=, and GET /reviews?item_id= (Stories 24, 25, 26, 27) | The dietary filter and the keyword search combine correctly, and reviews can now be read per dish, which closes the last customer-facing story. |
| Reporting - daily revenue, revenue trends, and low-performing dishes (Stories 10, 11, 14, 15) | Complaint comments from reviews rated 2 or lower show up next to the low-rated dishes, and the trends endpoint rejects an inverted date range with a 400. |

## Complete tasks

Mark work items “Done” that met acceptance criteria. For items that need more work, determine if they will move to the next sprint or back to the backlog.

- Done - all 75 points in the sprint were accepted, and nothing moved back to the product backlog:

  - Carryover: Story 8 (3 pts) view complete order details, Story 22 (5 pts) order tracking.

  - Inventory: Story 5 (3 pts) manual adjustment, Story 6 (5 pts) auto-disable out-of-stock items.

  - Manager reporting: Story 9 (3 pts) filter orders by date, Story 10 (5 pts) low-performing dishes, Story 11 (5 pts) complaint and review reasons.

  - Promotions: Story 12 (5 pts) create and manage promo codes, Story 28 (3 pts) apply a promo at checkout.

  - Checkout and fulfilment: Story 19 (3 pts) cash on delivery or pickup, Story 20 (3 pts) takeout or delivery, Story 21 (3 pts) estimated ready time, Story 23 (5 pts) real-time status updates.

  - Discovery and feedback: Story 24 (5 pts) dietary filter, Story 25 (3 pts) keyword search, Story 26 (5 pts) rate and review a dish.

  - Pulled in mid-sprint once the surrounding code made them cheap: Story 27 (3 pts) read other customers' reviews, Story 15 (5 pts) revenue trends over time, Story 17 (3 pts) optional account creation.

  - Technical task: in-memory test harness, api/seed.py demo data, and the documentation refresh.

- Also fixed while finishing the above, from the Sprint 1 review action items:

  - Order totals are computed server-side instead of being supplied by the client.

  - Line-item changes deduct and restore ingredient stock, with a 409 when stock is insufficient.

  - Negative prices and quantities are rejected with 422, and the price column was widened from DECIMAL(4,2) to DECIMAL(10,2).

  - Manager foreign keys on menu items and inventory are now validated instead of being silently dropped.

- Still in the product backlog - not started, and the only story left unbuilt:

  - Story 13 (3 pts) view promo code usage statistics.

## Upcoming

Add action items coming out of the sprint review meeting.

- Story 13 (promo code usage statistics) stays in the product backlog as the only remaining item.

- Move the development database from SQLite to MySQL so the deployment configuration matches the design document.

- Add authentication and authorisation so the manager-only endpoints are actually protected rather than open.

- Add pagination to GET /orders and GET /menuitems before the seeded dataset grows any further.

- Run the pytest suite in CI on every push so a regression is caught before it reaches main.